## vinay
Work Report:-12-14-2016
Name | Date | Module Work | Testing | Testing date
Vinay | 2016-12-14 | Report Module,bug file(complete) | Remain | 15-12-2016
| 15-12-2016 | Admin Panel and Bug File(Testing remain) | Remain

## Indrajit
Name | Date | Module Work | Testing | Testing Date
Indrajit | 14-12-2016 | Ticket module (complete) | Remain
| 15-12-2016 | solve ticket module issue | Remain | 15-12-2016

## Mitesh
Name | Date | Module Work | Testing | Testing Date
Mitesh | 14-12-2016 | Order module(Continue) | remain
| 15-12-2016 | Order module(Continue)

## Rajesh
Name | Date | Module work | Testing | Testing date
Rajesh | 14-12-2016 | ticket.php- scroll issue(done),Rienic - Design chnages done,stock - background image issue and responsive issue solved(done) |  | 15-12-2016
| 15-12-2016 | Work on logistic module design and R&D and wholebarofwax in create GIF image | done | 15-12-2016

## chirag
Name | date | Module work | Testing | Testing date
chirag | 14/12/2016 | mybeststockpicks.com(complete),lauha.sinikkali.com(complete) | Remain | 15-12-2016
| 15/12/2016 | wholebarofwax .com ask 1 :- Home page Content add Task 2 :- Video join cutter and set background in Home page Task 3 :- About Us page Content ,Logo And Right instend Menu Name add With Javascript Task 4 :- Our Industry Page Content And images Add | Remain | 15-12-2016

## sandip
Name | Date | Module Work | Testing | Testing Date
Sandip | 14-12-2016 | create mayloz report,Srapo,Test mayloz | done | 15-12-2016
| 15-12-2016 | ticket module,report(return,) | Remain(continue) | 15-12-2016
|  | wholebarofwax | done | 15-12-2016